## time_Lukas
Varga Lukas
|  | sum - hours of work: |  | 26:39 | lead developer | 0:00
# | date | start | end | duration | content of work
1 | 2021-08-06 | 11:00 | 12:15 | 1:15 | downloaded instructions & demo data; created timetable; updated Angular+Node, created new Angular project + GitHub repository; pushed basic node data via Git commands to repository; created GitHub Kanban Board
2 | 2021-08-06 | 16:30 | 17:15 | 0:45 | filled GitHub Kanban Board with todo's; created base form of protocol
3 | 2021-08-07 | 14:45 | 17:00 | 2:15 | generated components (login, register, faq, overview, tracking) and reused code from semester project for login + register + validation; generated routing
4 | 2021-08-07 | 19:00 | 20:00 | 1:00 | extended content of component register; thought about useful functions in db.js and app.js
5 | 2021-08-08 | 16:40 | 17:30 | 0:50 | installed password-hash and random-token modules for login; added login-requirement to enable overview and tracking only for logged in users; adapted register component;
6 | 2021-08-10 | 13:00 | 15:30 | 2:30 | overview component; debugging
7 | 2021-08-10 | 18:40 | 21:10 | 2:30 | updated overview + tracking component logic&html; adapting db.js + app.js; tested registration/login/overview functionality and debugged errors
8 | 2021-08-11 | 10:20 | 12:20 | 2:00 | googled + tried different time syntax to get chosen timestamp from timepicker AND timestamp from 'Check In' to calculate time difference until 'Check Out' and calculate fitting ending time to equal timepicker
9 | 2021-08-11 | 13:20 | 15:55 | 2:35 | finished logic (tracking will take room, date and time as input -> check-out and check-in appear and disappear as wanted; data will be saved in db and displayed on overview component)
10 | 2021-08-11 | 18:00 | 19:14 | 1:14 | tested functionality and debugged last errors; updated backend
11 | 2021-08-11 | 20:00 | 23:15 | 3:15 | created design for every component; added toggle to header; included choice between darkmode/lightmode
12 | 2021-08-12 | 18:00 | 20:20 | 2:20 | filled up FAQ with content (text + screenshots); added test data into db; started writing protocol
13 | 2021-08-13 | 9:10 | 10:20 | 1:10 | protocol 'technical steps' done; protocol 'application guidelines' part registration done
14 | 2021-08-14 | 0:10 | 1:30 | 1:20 | wrote protocol part 'application guidelines' for every component, accept 'track time', because I want to try using the json file for creating the dropdown => if successful I need to adapt db.js, overview.component.html and so forth
15 | 2021-08-14 | 9:55 | 11:20 | 1:25 | finished documentation
16 | 2021-08-14 | 14:25 | 14:40 | 0:15 | zip all needed files; upload to Moodle for grading
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
Thanks for participating!